## Sample Pediatric Quality Improvement Activity

## QI Activity: Increase the percentage of adolescents who receive annual depression screening and have a documented follow up plan when the screening is positive.

## Sample Goal: Increase percentage of adolescents aged 12-17 who receive an annual depression screen from X to X by December 31, 2026

QI activities to consider are listed below.  Best practice is to focus on one activity at a time so you can evaluate the effectiveness of the change.

Establishing champions:  identify providers and staff who will follow and lead efforts ensuring all staff and providers are engaged and updated

- Baseline data review: CY 2024 will be provided prior to January 2026. Established opportunities based on HCPF Practice Assessment Tool results

  - January 2026 they can access the Perform+ tool to assess baseline rates by provider and population.

- Workflow optimization: Determine the appropriate QI tool to support practice (PDSA, root cause analysis, etc.).

  - Activities may include: add EHR alerts for overdue screenings, make depression screening part of the standard vitals collection at all well visits, send the PHQ-9-A or PHQ-9 through patient portal for early completion, provide tablets in waiting room, determine processes to “catch” patients who are overdue such as - standing orders, huddles, universal screening at all visits

- Staff education and training: Provide all staff training on AAP guidelines around screening, provide staff opportunities for role play conversations to ‘normalize’ screening, share practice level data at monthly staff meetings to encourage progress

- Monitoring: review trends in the Perform+ tool, CPT coding rates, identify missed coding opportunities in QI meetings

- Patient engagement: de-stigmatize screening through waiting room posters, include information on screenings with pre-visit communications

Mid-Year goal may include:

- Standardized workflow for screening with the PHQ-9-A has been implemented and progress is monitored at staff meetings monthly with ongoing PDSA cycles as needed to reach our goal.

- Staff are trained and confident in their ability to introduce screening in a non-stigmatized manner with ongoing support to encourage continued improvement.

- We will have created a dashboard to easily monitor progress on this project and have processes to review with staff on at least a monthly basis.