Course Director Checklist – CME Office

|  |  | Responsibility |  | Timeline |
| --- | --- | --- | --- | --- |

|  |  | Complete a needs assessment |  | - 6 – 9 months prior to the proposed event a needs assessment should be conducted to determine professional practice gaps |
| --- | --- | --- | --- | --- |

|  |  | Pre-Application and planning committee |  | - Submit preapplication 5 - 6 months prior to the event - Disclosure forms from the planning committee members, course director and anyone in a position to control content are due with the preapplication. |
| --- | --- | --- | --- | --- |

|  |  | Activity Development Application |  | - Submit Activity Application 4 – 6 months in advance - Submit draft agenda with application - Discuss planned activity with Associate Dean of CME |
| --- | --- | --- | --- | --- |

|  |  | Service fee |  | - Please pay upon invoice receipt |
| --- | --- | --- | --- | --- |

|  |  | Agenda building |  | - Final agenda submission due at least 1 month prior to event |  |
| --- | --- | --- | --- | --- | --- |

|  |  | Commercial Support (Grants) and Letter of Agreement (LOA) |  | - Commercial support = financial or in-kind contributions given by a commercial interest (ineligible company) and used to pay all or part of the costs of a CME activity - Provide a list of all commercial support grants being pursued. - OCME acknowledges LOA, and CUSOM-Grants & Contracts & Company sign LOA prior to start of activity |
| --- | --- | --- | --- | --- |

|  |  | Faculty/Speaker Disclosures |  | - Submit ASAP. Disclosures from all faculty/contributors are due a minimum of 1 month prior to the CME event. Should be completed when speaker accepts invitation to participate, and include directions about avoiding bias in content - Failure to submit a disclosure form is equivalent to refusing to disclose and may result in disqualification of faculty and reduction of CME hours |
| --- | --- | --- | --- | --- |

|  |  | Promotional Materials and Marketing |  | - Promotional materials must be reviewed and approved by OCME; review promotion checklist for details - Exhibits/marketing info must be physically separated from the CME activity - No logos/slogans/pharmaceutical name brands in presentations or in conference booklets - Explicit permission is required to share participant information with commercial supporters/exhibitors |
| --- | --- | --- | --- | --- |

|  |  | Content Validation Form |  | - Collect educational materials such as slides and handouts ASAP (at least 1 month prior to course is recommended) - Review all materials for content bias and commercial bias, ensuring they do not contain advertising, trade names, logos, product messages, or clinical recommendations that are not evidence-based or standard of care |
| --- | --- | --- | --- | --- |
|  |  | Evaluation/CME Credit |  | - Participants, including course directors/planners, must complete evaluation to claim CME credit; all learner names, degrees, emails must be collected. |
|  |  | Final Documents |  | - Submit Final Attendee list ASAP and Income & Expense Statement within 1-2 months after event. |

12/6/24