## Gantt Chart
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8
Initial problem statement | bar: Month 1
Literature search to understand best practices | bar: Month 1 to Month 2
Begin to think about metrics and how they alight with goals of unit, institution, or at national level | bar: Month 1 to Month 2
Identify key stakeholders who must sign off on project | bar: Month 1 to Month 2
Reach out to positive and negative deviance projects | bar: Month 1 to Month 2
Create guiding coalition | bar: Month 1 to Month 2
Begin building sense of urgency | bar: Month 2 to Month 3
Complete voice of customer | bar: Month 2 to Month 4
Affinity diagram/RCA | bar: Month 2 to Month 4
Create current state process map | bar: Month 3 to Month 4
Identify process measures | bar: Month 1 to Month 4
Identify outcome measures, if relevant | bar: Month 1 to Month 4
Identify which data to track and finalize baseline data | bar: Month 1 to Month 4
Finalize problem statement AND aim statement | bar: Month 3 to Month 4
Revisit affinity diagram/RCA to formalize the pain points | bar: Month 5 to Month 6
Identify most impactful problems from RCA/affinity diagram | bar: Month 5 to Month 6
Brainstorm solutions | bar: Month 5 to Month 6
Create ideal state process map | bar: Month 5 to Month 6
Finalize which solution(s) to focus on | bar: Month 6 to Month 7
Create implementation plan with consideration of change management steps | bar: Month 6 to Month 7
Confirm data analysis plan | bar: Month 6 to Month 7
Implement at least one intervention | bar: Month 6 to Month 8
Ensure ongoing change management steps occuring | bar: Month 6 to Month 8
Present work | bar: Month 8
Problem Statement
Initial:
Final:
Aim Statement

## Goals by Month
Month One: Identify Your Problem and Team
Creat your problem statement
Literature search to understand best practices
Metrics or goals of unit, institution, or at national level
Identify any missing information from problem statement
Ensure sense of urgency for your project work
Identify colleagues who should be involved in your work (guiding coalition)
Ensure stakeholders have signed off
Month Two: Define and Scope
Complete voice of the customer
Finalize concise problem statement
Months Three, Four: Measure and Analyze
Identify what processes you will map out to help you understand your problem
Identify your process and outcome metrics
Plan for an event to understand your root causes (RCA or affinity diagram): who should attend? What format? When?
Complete process map
Complete RCA (fishbone diagram, affinity diagram, etc)
Identify pain points in the current processes
Months Five, Six: Design and Implement Interventions
Use the Pareto Principle to identify the most impactful contributing factors
Use design thinking, positive deviance, and heirarchy of interventions to identify 1-2 interventions that will address major contributing factors
Discuss your interventions and create an implementation plan: what changes will you make? Who needs to know about the change? How will you communicate this change? What resistance and barriers will you face and how can you address them? How will you celebrate short-term wins? How will you measure your outcomes and processes?
Finalize data plan
Finalize implementation plan
Month Seven: Interventions, con't
Implement at least one of your interventions
Analyze your data for impact
Make changes to intervention as needed based on data
Return to steps of change management: where are you facing resistance, why are they resisting, revisit 8 steps of change management to determine where to focus attention
Months Eight/Nine: Presentations
Create a presentation for IHQSE
Consider poster or abstract for work dissemination